## Description
Requirements Prioritization Model
Karl Wiegers
This spreadsheet contains a simple model for estimating the relative priorities of implementing
specific features or requirements in a software system. The "Example" worksheet contains an
example, from a project called the Chemical Tracking System. The worksheet called
"Template" contains several blank rows that contain all the formulas. To use this tool, copy
the "Template" worksheet into a new spreadsheet file and enter your own items to be prioritized,
copying and inserting blank rows as necessary to get enough space to handle all the items you
wish to prioritize in one pass.
The priority is considered to be a function of how desirable it is to include a specific feature
(where desirability considers both the benefit the feature would provide to the customer, and
the penalty you might incur in the customer's eyes if the feature is omitted), and both the
relative cost and technical risk associated with implementing the feature. Every proposed feature
is rated for each of the four dimensions (benefit, penalty, cost, risk) on a relative scale
of 1-9 (9 is high). You can also adjust the weighting factors for each of these four dimensions. For example,
if you feel that benefit is twice as important as penalty, which is the same importance as cost,
but risk is only half as important as cost, then you would use weighting factors (in row 1 of the
example) of 2, 1, 1, and 0.5, respectively.
After entering the relative numbers for all the features, the relative priority for each
feature is calculated by considering the percentage of the weighted feature desirability
(or value), cost, and risk attributable to each feature. If you sort the list of features
descending by the "Priority" column, the top priority items are at the top of the list.
You would not use this approach to estimate priorities for features that you know must be included,
for any reason (political, competitive advantage, regulatory or contractual requirement, etc.). Only
use this tool as a way to differentiate among requirements that are not on the list of "absolutely
must do"s.
The "Multiple Stakeholders" worksheet illustrates a refinement of the basic spreadsheet that accommodates
multiple stakeholders or user classes who have different ideas about requirement priorities. This example
handles three stakeholders. Each stakeholder has a separate pair of columns for rating benefit and penalty.
The numbers in row 1 indicate the relative weight that each stakeholder gets in the decision-making process.
Favored user classes get higher weighting factors. The spreadsheet incorporates those weights when it
calculates the overall benefit and penalty numbers for each proposed requirement. You can experiment
with the benefit and penalty values, and the weighting factors, in this worksheet to see the effect of different
stakeholder evaluations on the calculated priority numbers.
This spreadsheet is Copyright © 2013 by Karl Wiegers and Seilevel.
Permission is granted to use, modify, and distribute this spreadsheet file.
More information about the model can be found in Software Requirements, 3rd Edition by Karl Wiegers and Joy Beatty,
Microsoft Press, 2013

## 模版（中文）
相对权重： | 1 | 1 |  |  | 1 |  | 1
请在每个特性的相对收益、损失、风险、成本内输入1-9之间的数字，数字越大，收益越高、损失越大、成本越高、风险越高
特性 | 相对收益 | 相对损失 | 总价值 | 价值 % | 相对成本 | 成本 % | 相对风险 | 风险 % | 优先级
用户登录 | 9 | 9 | 18 | 1.5267 | 1 | 0.17153 | 1 | 0.18315 | 4.3045
用户注册 | 9 | 9 | 18 | 1.5267 | 2 | 0.34305 | 1 | 0.18315 | 2.9014
用户通过统一身份验证进行实名认证 | 5 | 9 | 14 | 1.1874 | 1 | 0.17153 | 3 | 0.54945 | 1.647
用户设置名称 | 4 | 4 | 8 | 0.67854 | 5 | 0.85763 | 3 | 0.54945 | 0.48223
用户设置头像 | 3 | 7 | 10 | 0.84818 | 7 | 1.2007 | 9 | 1.6484 | 0.29771
用户设置个人签名 | 2 | 5 | 7 | 0.59372 | 8 | 1.3722 | 1 | 0.18315 | 0.38173
用户设置个人信息 | 3 | 2 | 5 | 0.42409 | 3 | 0.51458 | 3 | 0.54945 | 0.39857
用户绑定手机号 | 6 | 2 | 8 | 0.67854 | 5 | 0.85763 | 2 | 0.3663 | 0.55439
用户找回密码 | 7 | 1 | 8 | 0.67854 | 3 | 0.51458 | 6 | 1.0989 | 0.42054
用户修改密码 | 7 | 1 | 8 | 0.67854 | 4 | 0.68611 | 3 | 0.54945 | 0.54918
用户修改昵称 | 2 | 4 | 6 | 0.50891 | 6 | 1.0292 | 7 | 1.2821 | 0.22019
用户修改头像 | 2 | 6 | 8 | 0.67854 | 8 | 1.3722 | 2 | 0.3663 | 0.3903
用户修改个性签名 | 1 | 2 | 3 | 0.25445 | 6 | 1.0292 | 6 | 1.0989 | 0.11957
用户修改个人信息 | 3 | 4 | 7 | 0.59372 | 8 | 1.3722 | 2 | 0.3663 | 0.34151
退出登录 | 7 | 6 | 13 | 1.1026 | 8 | 1.3722 | 5 | 0.91575 | 0.48193
用户个人资源空间上传资源 | 7 | 4 | 11 | 0.93299 | 1 | 0.17153 | 4 | 0.7326 | 1.0319
用户个人资源空间下载资源 | 7 | 7 | 14 | 1.1874 | 8 | 1.3722 | 7 | 1.2821 | 0.44737
用户播放视频 | 6 | 7 | 13 | 1.1026 | 4 | 0.68611 | 5 | 0.91575 | 0.68834
用户查看文档资源 | 5 | 3 | 8 | 0.67854 | 8 | 1.3722 | 6 | 1.0989 | 0.27459
用户查看课件资源 | 5 | 6 | 11 | 0.93299 | 6 | 1.0292 | 1 | 0.18315 | 0.7696
用户收藏板块 | 6 | 1 | 7 | 0.59372 | 2 | 0.34305 | 9 | 1.6484 | 0.29814
用户取消收藏板块 | 6 | 8 | 14 | 1.1874 | 5 | 0.85763 | 2 | 0.3663 | 0.97019
用户在板块中发布普通帖子 | 8 | 4 | 12 | 1.0178 | 5 | 0.85763 | 8 | 1.4652 | 0.43818
用户在板块中发布资源帖子 | 8 | 4 | 12 | 1.0178 | 6 | 1.0292 | 9 | 1.6484 | 0.38013
用户在帖子中回复 | 8 | 5 | 13 | 1.1026 | 8 | 1.3722 | 1 | 0.18315 | 0.70892
用户回复已有回复 | 8 | 3 | 11 | 0.93299 | 3 | 0.51458 | 2 | 0.3663 | 1.0592
用户在楼中楼内回复用户 | 7 | 1 | 8 | 0.67854 | 3 | 0.51458 | 1 | 0.18315 | 0.9725
用户在帖子内选择“只看楼主” | 4 | 4 | 8 | 0.67854 | 2 | 0.34305 | 8 | 1.4652 | 0.37525
用户排序帖子回复，按回复时间倒序排序 | 3 | 1 | 4 | 0.33927 | 5 | 0.85763 | 9 | 1.6484 | 0.13538
用户排序帖子回复，按回复时间正序排序 | 3 | 4 | 7 | 0.59372 | 9 | 1.5437 | 4 | 0.7326 | 0.26082
用户排序帖子回复，按点赞数排序 | 3 | 7 | 10 | 0.84818 | 4 | 0.68611 | 7 | 1.2821 | 0.43095
用户查看原图 | 3 | 7 | 10 | 0.84818 | 2 | 0.34305 | 2 | 0.3663 | 1.1957
用户保存图片 | 4 | 2 | 6 | 0.50891 | 4 | 0.68611 | 4 | 0.7326 | 0.35871
用户删除自己发布的帖子 | 5 | 4 | 9 | 0.76336 | 4 | 0.68611 | 8 | 1.4652 | 0.35483
用户点赞帖子 | 6 | 5 | 11 | 0.93299 | 9 | 1.5437 | 5 | 0.91575 | 0.37934
用户取消点赞帖子 | 6 | 3 | 9 | 0.76336 | 8 | 1.3722 | 3 | 0.54945 | 0.39724
用户点赞回复 | 4 | 1 | 5 | 0.42409 | 4 | 0.68611 | 5 | 0.91575 | 0.26475
用户取消点赞回复 | 4 | 3 | 7 | 0.59372 | 7 | 1.2007 | 1 | 0.18315 | 0.42904
用户收藏帖子 | 6 | 7 | 13 | 1.1026 | 1 | 0.17153 | 9 | 1.6484 | 0.60588
用户取消收藏帖子 | 6 | 9 | 15 | 1.2723 | 6 | 1.0292 | 8 | 1.4652 | 0.51006
用户分享帖子 | 3 | 7 | 10 | 0.84818 | 4 | 0.68611 | 9 | 1.6484 | 0.36333
用户分享板块 | 3 | 4 | 7 | 0.59372 | 4 | 0.68611 | 1 | 0.18315 | 0.68302
用户@其他用户 | 4 | 4 | 8 | 0.67854 | 4 | 0.68611 | 1 | 0.18315 | 0.7806
用户下载资源帖子的资源 | 7 | 5 | 12 | 1.0178 | 6 | 1.0292 | 5 | 0.91575 | 0.52332
用户把资源帖子的资源添加到个人资源空间 | 7 | 9 | 16 | 1.3571 | 9 | 1.5437 | 5 | 0.91575 | 0.55177
用户查看收藏的资源帖子 | 7 | 7 | 14 | 1.1874 | 6 | 1.0292 | 6 | 1.0989 | 0.55799
用户查看收藏帖子 | 7 | 5 | 12 | 1.0178 | 6 | 1.0292 | 2 | 0.3663 | 0.72937
用户通过ID搜索用户 | 5 | 5 | 10 | 0.84818 | 8 | 1.3722 | 7 | 1.2821 | 0.31955
用户查看其它用户个人信息 | 8 | 3 | 11 | 0.93299 | 4 | 0.68611 | 3 | 0.54945 | 0.75512
用户添加好友 | 6 | 8 | 14 | 1.1874 | 6 | 1.0292 | 7 | 1.2821 | 0.51378
用户删除好友 | 6 | 1 | 7 | 0.59372 | 1 | 0.17153 | 7 | 1.2821 | 0.40846
用户查看信息 | 6 | 9 | 15 | 1.2723 | 6 | 1.0292 | 7 | 1.2821 | 0.55048
用户拉黑其他用户 | 4 | 4 | 8 | 0.67854 | 9 | 1.5437 | 9 | 1.6484 | 0.21257
用户给好友发送私信 | 7 | 1 | 8 | 0.67854 | 5 | 0.85763 | 2 | 0.3663 | 0.55439
用户给非好友发送私信 | 7 | 3 | 10 | 0.84818 | 8 | 1.3722 | 1 | 0.18315 | 0.54532
用户在私信中发送图片 | 6 | 5 | 11 | 0.93299 | 2 | 0.34305 | 8 | 1.4652 | 0.51596
用户在私信中发送个人资源空间内的资源 | 7 | 4 | 11 | 0.93299 | 9 | 1.5437 | 5 | 0.91575 | 0.37934
用户在私信中发送本地资源、文件 | 7 | 2 | 9 | 0.76336 | 1 | 0.17153 | 9 | 1.6484 | 0.41946
用户举报私信消息 | 2 | 1 | 3 | 0.25445 | 3 | 0.51458 | 2 | 0.3663 | 0.28886
用户在群聊内发送文字 | 8 | 5 | 13 | 1.1026 | 2 | 0.34305 | 3 | 0.54945 | 1.2354
用户在群聊内发送图片 | 8 | 9 | 17 | 1.4419 | 6 | 1.0292 | 9 | 1.6484 | 0.53852
用户在群聊内@他人 | 6 | 2 | 8 | 0.67854 | 1 | 0.17153 | 9 | 1.6484 | 0.37285
用户在群聊内发送个人资源空间内的资源 | 5 | 9 | 14 | 1.1874 | 4 | 0.68611 | 2 | 0.3663 | 1.1283
用户在群聊内发送本地资源、文件 | 5 | 6 | 11 | 0.93299 | 4 | 0.68611 | 4 | 0.7326 | 0.65764
用户举报群聊消息 | 2 | 4 | 6 | 0.50891 | 8 | 1.3722 | 8 | 1.4652 | 0.17936
用户创建群聊 | 4 | 4 | 8 | 0.67854 | 8 | 1.3722 | 6 | 1.0989 | 0.27459
用户邀请好友加入群聊 | 4 | 1 | 5 | 0.42409 | 3 | 0.51458 | 1 | 0.18315 | 0.60781
用户查看私信 | 7 | 8 | 15 | 1.2723 | 4 | 0.68611 | 2 | 0.3663 | 1.2089
用户进入首页 | 9 | 9 | 18 | 1.5267 | 8 | 1.3722 | 4 | 0.7326 | 0.72535
用户进入某一板块 | 9 | 7 | 16 | 1.3571 | 7 | 1.2007 | 6 | 1.0989 | 0.59014
用户查看板块资源 | 8 | 2 | 10 | 0.84818 | 8 | 1.3722 | 5 | 0.91575 | 0.37071
用户查看板块帖子 | 8 | 7 | 15 | 1.2723 | 7 | 1.2007 | 3 | 0.54945 | 0.72695
用户查看板块热门帖子 | 8 | 4 | 12 | 1.0178 | 9 | 1.5437 | 4 | 0.7326 | 0.44713
用户全局搜索帖子 | 7 | 1 | 8 | 0.67854 | 4 | 0.68611 | 2 | 0.3663 | 0.64475
用户在板块中搜索帖子 | 7 | 1 | 8 | 0.67854 | 3 | 0.51458 | 5 | 0.91575 | 0.47439
用户全局排序帖子 | 4 | 9 | 13 | 1.1026 | 7 | 1.2007 | 8 | 1.4652 | 0.41361
用户在板块中排序帖子 | 4 | 8 | 12 | 1.0178 | 7 | 1.2007 | 1 | 0.18315 | 0.7355
用户全局筛选帖子 | 4 | 5 | 9 | 0.76336 | 3 | 0.51458 | 1 | 0.18315 | 1.0941
用户在板块中筛选帖子 | 4 | 3 | 7 | 0.59372 | 6 | 1.0292 | 1 | 0.18315 | 0.48975
用户关注板块 | 5 | 8 | 13 | 1.1026 | 8 | 1.3722 | 7 | 1.2821 | 0.41542
用户关注其他用户 | 5 | 7 | 12 | 1.0178 | 6 | 1.0292 | 3 | 0.54945 | 0.64475
用户拉黑其他用户 | 2 | 9 | 11 | 0.93299 | 2 | 0.34305 | 2 | 0.3663 | 1.3153
用户举报其他用户 | 2 | 4 | 6 | 0.50891 | 1 | 0.17153 | 9 | 1.6484 | 0.27964
用户举报帖子 | 2 | 8 | 10 | 0.84818 | 7 | 1.2007 | 7 | 1.2821 | 0.34163
用户查看友情链接 | 7 | 9 | 16 | 1.3571 | 1 | 0.17153 | 9 | 1.6484 | 0.7457
用户查看APP导向使用指南 | 7 | 1 | 8 | 0.67854 | 7 | 1.2007 | 3 | 0.54945 | 0.38771
用户查看板块资源版面 | 8 | 6 | 14 | 1.1874 | 1 | 0.17153 | 4 | 0.7326 | 1.3134
用户查看版面 | 8 | 5 | 13 | 1.1026 | 9 | 1.5437 | 2 | 0.3663 | 0.57728
用户查看帖子浏览历史 | 5 | 4 | 9 | 0.76336 | 7 | 1.2007 | 5 | 0.91575 | 0.36068
用户按时间排序帖子 | 4 | 6 | 10 | 0.84818 | 8 | 1.3722 | 3 | 0.54945 | 0.44138
用户按回复顺序排序帖子 | 4 | 6 | 10 | 0.84818 | 6 | 1.0292 | 3 | 0.54945 | 0.53729
用户按智能热度顺序排序帖子 | 4 | 3 | 7 | 0.59372 | 4 | 0.68611 | 9 | 1.6484 | 0.25433
用户在首页查看关注板块、用户的新帖子 | 7 | 2 | 9 | 0.76336 | 1 | 0.17153 | 9 | 1.6484 | 0.41946
教师发布无内容长度、图片数量限制的贴子 | 7 | 4 | 11 | 0.93299 | 6 | 1.0292 | 8 | 1.4652 | 0.37404
教师编辑帖子 | 6 | 5 | 11 | 0.93299 | 1 | 0.17153 | 7 | 1.2821 | 0.64186
教师查询用户真实信息 | 6 | 5 | 11 | 0.93299 | 6 | 1.0292 | 2 | 0.3663 | 0.66859
教师进入团队板块进行指导 | 5 | 2 | 7 | 0.59372 | 7 | 1.2007 | 4 | 0.7326 | 0.30711
管理员添加板块 | 6 | 8 | 14 | 1.1874 | 1 | 0.17153 | 7 | 1.2821 | 0.81691
管理员删除板块 | 6 | 6 | 12 | 1.0178 | 7 | 1.2007 | 1 | 0.18315 | 0.7355
管理员修改板块 | 6 | 7 | 13 | 1.1026 | 9 | 1.5437 | 7 | 1.2821 | 0.3902
管理员删除帖子 | 7 | 5 | 12 | 1.0178 | 3 | 0.51458 | 7 | 1.2821 | 0.56651
管理员发布全局通知 | 7 | 6 | 13 | 1.1026 | 1 | 0.17153 | 3 | 0.54945 | 1.5294
管理员发布板块通知 | 6 | 4 | 10 | 0.84818 | 5 | 0.85763 | 5 | 0.91575 | 0.47828
管理员在论坛板块中置顶帖子 | 5 | 1 | 6 | 0.50891 | 2 | 0.34305 | 3 | 0.54945 | 0.5702
管理员在论坛板块中置顶帖子 | 5 | 4 | 9 | 0.76336 | 2 | 0.34305 | 6 | 1.0989 | 0.52939
管理员解封用户 | 4 | 7 | 11 | 0.93299 | 3 | 0.51458 | 7 | 1.2821 | 0.5193
管理员给板块添加版面 | 6 | 1 | 7 | 0.59372 | 6 | 1.0292 | 8 | 1.4652 | 0.23803
管理员编辑自己的帖子 | 5 | 1 | 6 | 0.50891 | 9 | 1.5437 | 2 | 0.3663 | 0.26644
管理员编辑其他用户的帖子 | 7 | 2 | 9 | 0.76336 | 5 | 0.85763 | 7 | 1.2821 | 0.35676
管理员移动帖子的版面 | 6 | 9 | 15 | 1.2723 | 3 | 0.51458 | 4 | 0.7326 | 1.0201
管理员给帖子设置精品 | 5 | 6 | 11 | 0.93299 | 4 | 0.68611 | 1 | 0.18315 | 1.0733
管理员解散群聊 | 4 | 6 | 10 | 0.84818 | 3 | 0.51458 | 2 | 0.3663 | 0.96287
游客注册 | 5 | 1 | 6 | 0.50891 | 8 | 1.3722 | 6 | 1.0989 | 0.20594
游客浏览帖子 | 5 | 4 | 9 | 0.76336 | 9 | 1.5437 | 3 | 0.54945 | 0.36469
游客浏览资源 | 5 | 3 | 8 | 0.67854 | 6 | 1.0292 | 9 | 1.6484 | 0.25342
| 632 | 547 | 1179 | 100 | 583 | 100 | 546 | 100 | 70.699

## Template
Relative Weights: | 1 | 1 |  |  | 1 |  | 1
Feature | Relative Benefit | Relative Penalty | Total Value | Value % | Relative Cost | Cost % | Relative Risk | Risk % | Priority
<List each feature, requirement, or use case to be prioritized |  |  | 0 | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0!
in these cells, one item per cell. Copy and insert additional |  |  | 0 | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0!
rows as needed; the formulas will adjust automatically.> |  |  | 0 | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0!
|  |  | 0 | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0!
Totals | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0!

## Example
Relative Weights: | 2 | 1 |  |  | 1 |  | 0.5
Feature | Relative Benefit | Relative Penalty | Total Value | Value % | Relative Cost | Cost % | Relative Risk | Risk % | Priority
Print a material safety data sheet | 2 | 4 | 8 | 5.1613 | 1 | 2.7027 | 1 | 3.0303 | 1.2237
Query status of a vendor order | 5 | 3 | 13 | 8.3871 | 2 | 5.4054 | 1 | 3.0303 | 1.2119
Generate a Chemical Stockroom inventory report | 9 | 7 | 25 | 16.129 | 5 | 13.5135 | 3 | 9.0909 | 0.89313
See history of a specific chemical container | 5 | 5 | 15 | 9.6774 | 3 | 8.1081 | 2 | 6.0606 | 0.86883
Search vendor catalogs for a specific chemical | 9 | 8 | 26 | 16.7742 | 3 | 8.1081 | 8 | 24.2424 | 0.8292
Maintain a list of hazardous chemicals | 3 | 9 | 15 | 9.6774 | 3 | 8.1081 | 4 | 12.1212 | 0.68301
Modify a pending chemical request | 4 | 3 | 11 | 7.0968 | 3 | 8.1081 | 2 | 6.0606 | 0.63714
Generate an individual laboratory inventory report | 6 | 2 | 14 | 9.0323 | 4 | 10.8108 | 3 | 9.0909 | 0.58818
Check training database for hazardous chemical training record | 3 | 4 | 10 | 6.4516 | 4 | 10.8108 | 2 | 6.0606 | 0.46612
Import chemical structures from structure drawing tools | 7 | 4 | 18 | 11.6129 | 9 | 24.3243 | 7 | 21.2121 | 0.33246
Totals | 53 | 49 | 155 | 100 | 37 | 100 | 33 | 100

## Multiple Stakeholders
Relative Weights: | 3 |  | 1 |  | 1 |  | 1 | 1 |  |  | 1 |  | 1
| Stakeholder 1 |  | Stakeholder 2 |  | Stakeholder 3
Feature | Relative Benefit | Relative Penalty | Relative Benefit | Relative Penalty | Relative Benefit | Relative Penalty | Total Benefit | Total Penalty | Total Value | Value % | Relative Cost | Cost % | Relative Risk | Risk % | Priority
Query status of a vendor order | 7 | 3 | 5 | 3 | 5 | 3 | 6.2 | 3 | 9.2 | 9.4262 | 2 | 4.7619 | 1 | 3.0303 | 1.2097
Generate a Chemical Stockroom inventory report | 3 | 7 | 9 | 7 | 9 | 7 | 5.4 | 7 | 12.4 | 12.7049 | 5 | 11.9048 | 3 | 9.0909 | 0.60512
See history of a specific chemical container | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 10 | 10.2459 | 3 | 7.1429 | 2 | 6.0606 | 0.776
Print a chemical safety datasheet | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 3.0738 | 1 | 2.381 | 1 | 3.0303 | 0.56803
Maintain a list of hazardous chemicals | 4 | 9 | 4 | 9 | 4 | 9 | 4 | 9 | 13 | 13.3197 | 4 | 9.5238 | 4 | 12.1212 | 0.61537
Modify a pending chemical request | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 7 | 7.1721 | 3 | 7.1429 | 2 | 6.0606 | 0.5432
Generate an individual laboratory inventory report | 6 | 2 | 6 | 2 | 6 | 2 | 6 | 2 | 8 | 8.1967 | 4 | 9.5238 | 3 | 9.0909 | 0.44034
Search vendor catalogs for a specific chemical | 9 | 8 | 9 | 8 | 9 | 8 | 9 | 8 | 17 | 17.418 | 7 | 16.6667 | 8 | 24.2424 | 0.42577
Check training database for hazardous chemical training record | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 7 | 7.1721 | 4 | 9.5238 | 2 | 6.0606 | 0.46021
Import chemical structures from structure drawing tools | 7 | 4 | 7 | 4 | 7 | 4 | 7 | 4 | 11 | 11.2705 | 9 | 21.4286 | 7 | 21.2121 | 0.26431
Totals | 50 | 46 | 54 | 46 | 54 | 46 | 51.6 | 46 | 97.6 | 100 | 42 | 100 | 33 | 100

## Sheet1
特性 | 相对收益 | 相对损失 | 总价值 | 价值 % | 相对成本 | 成本 % | 相对风险 | 风险 % | 优先级
用户登录 | 9 | 9 | 18 | 1.495 | 1 | 0.17699 | 1 | 0.18692 | 4.1082
用户注册 | 9 | 9 | 18 | 1.495 | 2 | 0.35398 | 1 | 0.18692 | 2.764
用户在板块中发布普通帖子 | 8 | 9 | 17 | 1.412 | 2 | 0.35398 | 2 | 0.37383 | 1.94
用户个人资源空间上传资源 | 7 | 9 | 16 | 1.3289 | 2 | 0.35398 | 2 | 0.37383 | 1.8259
用户在楼中楼内回复用户 | 7 | 9 | 16 | 1.3289 | 2 | 0.35398 | 2 | 0.37383 | 1.8259
用户全局排序帖子 | 4 | 4 | 8 | 0.66445 | 1 | 0.17699 | 1 | 0.18692 | 1.8259
用户在帖子中回复 | 8 | 3 | 11 | 0.91362 | 2 | 0.35398 | 1 | 0.18692 | 1.6891
用户分享帖子 | 3 | 8 | 11 | 0.91362 | 2 | 0.35398 | 1 | 0.18692 | 1.6891
用户给非好友发送私信 | 7 | 6 | 13 | 1.0797 | 3 | 0.53097 | 1 | 0.18692 | 1.504
用户在私信中发送图片 | 6 | 5 | 11 | 0.91362 | 2 | 0.35398 | 2 | 0.37383 | 1.2553
用户在群聊内发送图片 | 8 | 8 | 16 | 1.3289 | 3 | 0.53097 | 3 | 0.56075 | 1.2173
用户查看板块资源 | 8 | 5 | 13 | 1.0797 | 2 | 0.35398 | 3 | 0.56075 | 1.1804
用户查看私信 | 7 | 6 | 13 | 1.0797 | 1 | 0.17699 | 4 | 0.74766 | 1.1677
用户给好友发送私信 | 7 | 8 | 15 | 1.2458 | 5 | 0.88496 | 1 | 0.18692 | 1.1623
用户关注其他用户 | 5 | 9 | 14 | 1.1628 | 4 | 0.70796 | 2 | 0.37383 | 1.0749
用户在私信中发送个人资源空间内的资源 | 7 | 9 | 16 | 1.3289 | 3 | 0.53097 | 4 | 0.74766 | 1.0393
教师编辑帖子 | 6 | 9 | 15 | 1.2458 | 6 | 1.0619 | 1 | 0.18692 | 0.99759
用户在板块中发布资源帖子 | 8 | 6 | 14 | 1.1628 | 5 | 0.88496 | 2 | 0.37383 | 0.92374
用户查看帖子浏览历史 | 5 | 1 | 6 | 0.49834 | 2 | 0.35398 | 1 | 0.18692 | 0.92132
用户查看APP导向使用指南 | 7 | 4 | 11 | 0.91362 | 5 | 0.88496 | 1 | 0.18692 | 0.85236
管理员编辑其他用户的帖子 | 7 | 8 | 15 | 1.2458 | 3 | 0.53097 | 5 | 0.93458 | 0.85009
用户查看友情链接 | 7 | 8 | 15 | 1.2458 | 2 | 0.35398 | 6 | 1.1215 | 0.84437
管理员给帖子设置精品 | 5 | 8 | 13 | 1.0797 | 1 | 0.17699 | 6 | 1.1215 | 0.83153
游客浏览帖子 | 5 | 4 | 9 | 0.74751 | 2 | 0.35398 | 3 | 0.56075 | 0.81719
用户回复已有回复 | 8 | 8 | 16 | 1.3289 | 3 | 0.53097 | 6 | 1.1215 | 0.80419
用户按回复顺序排序帖子 | 4 | 8 | 12 | 0.99668 | 2 | 0.35398 | 5 | 0.93458 | 0.77348
用户收藏板块 | 6 | 9 | 15 | 1.2458 | 3 | 0.53097 | 6 | 1.1215 | 0.75393
用户在私信中发送本地资源、文件 | 7 | 8 | 15 | 1.2458 | 3 | 0.53097 | 6 | 1.1215 | 0.75393
用户在板块中排序帖子 | 4 | 7 | 11 | 0.91362 | 6 | 1.0619 | 1 | 0.18692 | 0.73156
用户取消点赞帖子 | 6 | 8 | 14 | 1.1628 | 5 | 0.88496 | 4 | 0.74766 | 0.71222
用户设置个人签名 | 2 | 9 | 11 | 0.91362 | 2 | 0.35398 | 5 | 0.93458 | 0.70902
用户播放视频 | 6 | 9 | 15 | 1.2458 | 4 | 0.70796 | 6 | 1.1215 | 0.68099
用户找回密码 | 7 | 9 | 16 | 1.3289 | 8 | 1.4159 | 3 | 0.56075 | 0.67229
用户添加好友 | 6 | 7 | 13 | 1.0797 | 6 | 1.0619 | 3 | 0.56075 | 0.6654
用户查看收藏的资源帖子 | 7 | 3 | 10 | 0.83056 | 5 | 0.88496 | 2 | 0.37383 | 0.65981
用户查看板块热门帖子 | 8 | 9 | 17 | 1.412 | 3 | 0.53097 | 9 | 1.6822 | 0.63797
用户取消收藏板块 | 6 | 2 | 8 | 0.66445 | 4 | 0.70796 | 2 | 0.37383 | 0.61421
管理员发布全局通知 | 7 | 5 | 12 | 0.99668 | 3 | 0.53097 | 6 | 1.1215 | 0.60314
管理员发布板块通知 | 6 | 3 | 9 | 0.74751 | 6 | 1.0619 | 1 | 0.18692 | 0.59855
用户设置名称 | 4 | 9 | 13 | 1.0797 | 4 | 0.70796 | 6 | 1.1215 | 0.59019
用户在群聊内发送本地资源、文件 | 5 | 4 | 9 | 0.74751 | 2 | 0.35398 | 5 | 0.93458 | 0.58011
用户全局筛选帖子 | 4 | 5 | 9 | 0.74751 | 2 | 0.35398 | 5 | 0.93458 | 0.58011
用户查看板块资源版面 | 8 | 6 | 14 | 1.1628 | 3 | 0.53097 | 8 | 1.4953 | 0.57385
用户查看板块帖子 | 8 | 2 | 10 | 0.83056 | 4 | 0.70796 | 4 | 0.74766 | 0.57059
用户进入某一板块 | 9 | 7 | 16 | 1.3289 | 8 | 1.4159 | 5 | 0.93458 | 0.56537
用户取消收藏帖子 | 6 | 5 | 11 | 0.91362 | 3 | 0.53097 | 6 | 1.1215 | 0.55288
用户下载资源帖子的资源 | 7 | 6 | 13 | 1.0797 | 6 | 1.0619 | 5 | 0.93458 | 0.54081
游客浏览资源 | 5 | 9 | 14 | 1.1628 | 8 | 1.4159 | 4 | 0.74766 | 0.53744
教师查询用户真实信息 | 6 | 1 | 7 | 0.5814 | 3 | 0.53097 | 3 | 0.56075 | 0.53255
用户点赞帖子 | 6 | 1 | 7 | 0.5814 | 2 | 0.35398 | 4 | 0.74766 | 0.52775
用户查看文档资源 | 5 | 9 | 14 | 1.1628 | 3 | 0.53097 | 9 | 1.6822 | 0.52538
教师进入团队板块进行指导 | 5 | 3 | 8 | 0.66445 | 3 | 0.53097 | 4 | 0.74766 | 0.51966
管理员添加板块 | 6 | 2 | 8 | 0.66445 | 3 | 0.53097 | 4 | 0.74766 | 0.51966
用户修改头像 | 2 | 8 | 10 | 0.83056 | 8 | 1.4159 | 1 | 0.18692 | 0.51818
用户个人资源空间下载资源 | 7 | 5 | 12 | 0.99668 | 9 | 1.5929 | 2 | 0.37383 | 0.50676
用户在板块中搜索帖子 | 7 | 5 | 12 | 0.99668 | 9 | 1.5929 | 2 | 0.37383 | 0.50676
用户把资源帖子的资源添加到个人资源空间 | 7 | 7 | 14 | 1.1628 | 8 | 1.4159 | 5 | 0.93458 | 0.4947
教师发布无内容长度、图片数量限制的贴子 | 7 | 6 | 13 | 1.0797 | 3 | 0.53097 | 9 | 1.6822 | 0.48786
用户修改昵称 | 2 | 7 | 9 | 0.74751 | 7 | 1.2389 | 2 | 0.37383 | 0.46349
用户进入首页 | 9 | 1 | 10 | 0.83056 | 6 | 1.0619 | 4 | 0.74766 | 0.45897
退出登录 | 7 | 5 | 12 | 0.99668 | 7 | 1.2389 | 5 | 0.93458 | 0.45856
用户查看课件资源 | 5 | 9 | 14 | 1.1628 | 8 | 1.4159 | 6 | 1.1215 | 0.45826
用户查看版面 | 8 | 5 | 13 | 1.0797 | 7 | 1.2389 | 6 | 1.1215 | 0.45743
用户举报其他用户 | 2 | 8 | 10 | 0.83056 | 4 | 0.70796 | 6 | 1.1215 | 0.45399
用户修改个人信息 | 3 | 8 | 11 | 0.91362 | 3 | 0.53097 | 8 | 1.4953 | 0.45088
用户举报帖子 | 2 | 7 | 9 | 0.74751 | 1 | 0.17699 | 8 | 1.4953 | 0.44699
管理员编辑自己的帖子 | 5 | 6 | 11 | 0.91362 | 8 | 1.4159 | 4 | 0.74766 | 0.42227
管理员移动帖子的版面 | 6 | 4 | 10 | 0.83056 | 8 | 1.4159 | 3 | 0.56075 | 0.42018
用户关注板块 | 5 | 4 | 9 | 0.74751 | 9 | 1.5929 | 1 | 0.18692 | 0.41999
用户取消点赞回复 | 4 | 5 | 9 | 0.74751 | 5 | 0.88496 | 5 | 0.93458 | 0.41082
管理员给板块添加版面 | 6 | 1 | 7 | 0.5814 | 7 | 1.2389 | 1 | 0.18692 | 0.40775
用户修改个性签名 | 1 | 6 | 7 | 0.5814 | 5 | 0.88496 | 3 | 0.56075 | 0.40215
用户在群聊内发送文字 | 8 | 6 | 14 | 1.1628 | 8 | 1.4159 | 8 | 1.4953 | 0.39941
用户通过ID搜索用户 | 5 | 1 | 6 | 0.49834 | 5 | 0.88496 | 2 | 0.37383 | 0.39589
用户绑定手机号 | 6 | 1 | 7 | 0.5814 | 2 | 0.35398 | 6 | 1.1215 | 0.39404
用户创建群聊 | 4 | 6 | 10 | 0.83056 | 9 | 1.5929 | 3 | 0.56075 | 0.38565
用户修改密码 | 7 | 4 | 11 | 0.91362 | 6 | 1.0619 | 7 | 1.3084 | 0.38544
用户排序帖子回复，按回复时间倒序排序 | 3 | 2 | 5 | 0.41528 | 3 | 0.53097 | 3 | 0.56075 | 0.38039
用户查看收藏帖子 | 7 | 2 | 9 | 0.74751 | 7 | 1.2389 | 4 | 0.74766 | 0.37627
用户设置个人信息 | 3 | 2 | 5 | 0.41528 | 1 | 0.17699 | 5 | 0.93458 | 0.3736
用户保存图片 | 4 | 1 | 5 | 0.41528 | 1 | 0.17699 | 5 | 0.93458 | 0.3736
用户删除好友 | 6 | 2 | 8 | 0.66445 | 5 | 0.88496 | 5 | 0.93458 | 0.36518
用户查看信息 | 6 | 8 | 14 | 1.1628 | 9 | 1.5929 | 9 | 1.6822 | 0.35503
用户在群聊内@他人 | 6 | 1 | 7 | 0.5814 | 4 | 0.70796 | 5 | 0.93458 | 0.35396
管理员删除帖子 | 7 | 3 | 10 | 0.83056 | 5 | 0.88496 | 8 | 1.4953 | 0.34894
用户在板块中筛选帖子 | 4 | 3 | 7 | 0.5814 | 1 | 0.17699 | 8 | 1.4953 | 0.34766
用户删除自己发布的帖子 | 5 | 1 | 6 | 0.49834 | 4 | 0.70796 | 4 | 0.74766 | 0.34235
用户收藏帖子 | 6 | 3 | 9 | 0.74751 | 6 | 1.0619 | 6 | 1.1215 | 0.34235
用户点赞回复 | 4 | 5 | 9 | 0.74751 | 4 | 0.70796 | 8 | 1.4953 | 0.33927
用户实名认证 | 5 | 3 | 8 | 0.66445 | 9 | 1.5929 | 2 | 0.37383 | 0.33784
用户邀请好友加入群聊 | 4 | 7 | 11 | 0.91362 | 9 | 1.5929 | 6 | 1.1215 | 0.33658
管理员解封用户 | 4 | 7 | 11 | 0.91362 | 9 | 1.5929 | 6 | 1.1215 | 0.33658
用户举报私信消息 | 2 | 3 | 5 | 0.41528 | 6 | 1.0619 | 1 | 0.18692 | 0.33253
用户分享板块 | 3 | 9 | 12 | 0.99668 | 9 | 1.5929 | 8 | 1.4953 | 0.32273
游客注册 | 5 | 4 | 9 | 0.74751 | 6 | 1.0619 | 7 | 1.3084 | 0.31536
管理员删除板块 | 6 | 5 | 11 | 0.91362 | 9 | 1.5929 | 7 | 1.3084 | 0.3149
用户查看其它用户个人信息 | 8 | 1 | 9 | 0.74751 | 4 | 0.70796 | 9 | 1.6822 | 0.31274
用户全局搜索帖子 | 7 | 2 | 9 | 0.74751 | 6 | 1.0619 | 8 | 1.4953 | 0.29231
用户在首页查看关注板块、用户的新帖子 | 7 | 3 | 10 | 0.83056 | 9 | 1.5929 | 8 | 1.4953 | 0.26894
用户@其他用户 | 4 | 3 | 7 | 0.5814 | 7 | 1.2389 | 5 | 0.93458 | 0.26749
管理员修改板块 | 6 | 1 | 7 | 0.5814 | 7 | 1.2389 | 5 | 0.93458 | 0.26749
用户查看原图 | 3 | 2 | 5 | 0.41528 | 2 | 0.35398 | 7 | 1.3084 | 0.24981
用户在群聊内发送个人资源空间内的资源 | 5 | 2 | 7 | 0.5814 | 9 | 1.5929 | 4 | 0.74766 | 0.2484
用户拉黑其他用户 | 2 | 6 | 8 | 0.66445 | 6 | 1.0619 | 9 | 1.6822 | 0.24213
用户排序帖子回复，按点赞数排序 | 3 | 1 | 4 | 0.33223 | 7 | 1.2389 | 1 | 0.18692 | 0.233
用户按智能热度顺序排序帖子 | 4 | 3 | 7 | 0.5814 | 9 | 1.5929 | 6 | 1.1215 | 0.21419
管理员在论坛板块中置顶帖子 | 5 | 2 | 7 | 0.5814 | 7 | 1.2389 | 8 | 1.4953 | 0.21263
用户举报群聊消息 | 2 | 3 | 5 | 0.41528 | 9 | 1.5929 | 3 | 0.56075 | 0.19283
用户设置头像 | 3 | 3 | 6 | 0.49834 | 6 | 1.0619 | 9 | 1.6822 | 0.1816
管理员解散群聊 | 4 | 2 | 6 | 0.49834 | 6 | 1.0619 | 9 | 1.6822 | 0.1816
用户拉黑其他用户 | 4 | 1 | 5 | 0.41528 | 4 | 0.70796 | 9 | 1.6822 | 0.17374
管理员在论坛板块中置顶帖子 | 5 | 1 | 6 | 0.49834 | 8 | 1.4159 | 8 | 1.4953 | 0.17118
用户排序帖子回复，按回复时间正序排序 | 3 | 1 | 4 | 0.33223 | 6 | 1.0619 | 5 | 0.93458 | 0.1664
用户按时间排序帖子 | 4 | 1 | 5 | 0.41528 | 7 | 1.2389 | 7 | 1.3084 | 0.16303
用户在帖子内选择“只看楼主” | 4 | 1 | 5 | 0.41528 | 7 | 1.2389 | 8 | 1.4953 | 0.15188