## Description
Requirements Prioritization Model
Karl Wiegers
This spreadsheet contains a simple model for estimating the relative priorities of implementing
specific features or requirements in a software system. The "Example" worksheet contains an
example, from a project called the Chemical Tracking System. The worksheet called
"Template" contains several blank rows that contain all the formulas. To use this tool, copy
the "Template" worksheet into a new spreadsheet file and enter your own items to be prioritized,
copying and inserting blank rows as necessary to get enough space to handle all the items you
wish to prioritize in one pass.
The priority is considered to be a function of how desirable it is to include a specific feature
(where desirability considers both the benefit the feature would provide to the customer, and
the penalty you might incur in the customer's eyes if the feature is omitted), and both the
relative cost and technical risk associated with implementing the feature. Every proposed feature
is rated for each of the four dimensions (benefit, penalty, cost, risk) on a relative scale
of 1-9 (9 is high). You can also adjust the weighting factors for each of these four dimensions. For example,
if you feel that benefit is twice as important as penalty, which is the same importance as cost,
but risk is only half as important as cost, then you would use weighting factors (in row 1 of the
example) of 2, 1, 1, and 0.5, respectively.
After entering the relative numbers for all the features, the relative priority for each
feature is calculated by considering the percentage of the weighted feature desirability
(or value), cost, and risk attributable to each feature. If you sort the list of features
descending by the "Priority" column, the top priority items are at the top of the list.
You would not use this approach to estimate priorities for features that you know must be included,
for any reason (political, competitive advantage, regulatory or contractual requirement, etc.). Only
use this tool as a way to differentiate among requirements that are not on the list of "absolutely
must do"s.
The "Multiple Stakeholders" worksheet illustrates a refinement of the basic spreadsheet that accommodates
multiple stakeholders or user classes who have different ideas about requirement priorities. This example
handles three stakeholders. Each stakeholder has a separate pair of columns for rating benefit and penalty.
The numbers in row 1 indicate the relative weight that each stakeholder gets in the decision-making process.
Favored user classes get higher weighting factors. The spreadsheet incorporates those weights when it
calculates the overall benefit and penalty numbers for each proposed requirement. You can experiment
with the benefit and penalty values, and the weighting factors, in this worksheet to see the effect of different
stakeholder evaluations on the calculated priority numbers.
This spreadsheet is Copyright © 2013 by Karl Wiegers and Seilevel.
Permission is granted to use, modify, and distribute this spreadsheet file.
More information about the model can be found in Software Requirements, 3rd Edition by Karl Wiegers and Joy Beatty,
Microsoft Press, 2013

## 模版（中文）
相对权重： | 1 | 1 |  |  | 1 |  | 1
请在每个特性的相对收益、损失、风险、成本内输入1-9之间的数字，数字越大，收益越高、损失越大、成本越高、风险越高
特性 | 相对收益 | 相对损失 | 总价值 | 价值 % | 相对成本 | 成本 % | 相对风险 | 风险 % | 优先级
用户登录 | 7 | 7 | 14 | 1.2567 | 6 | 1.0256 | 9 | 1.6014 | 0.47838
用户注册 | 4 | 8 | 12 | 1.0772 | 5 | 0.8547 | 2 | 0.35587 | 0.88983
用户通过统一身份验证进行实名认证 | 6 | 7 | 13 | 1.167 | 8 | 1.3675 | 8 | 1.4235 | 0.41812
用户设置名称 | 1 | 9 | 10 | 0.89767 | 2 | 0.34188 | 6 | 1.0676 | 0.63687
用户设置头像 | 4 | 4 | 8 | 0.71813 | 5 | 0.8547 | 2 | 0.35587 | 0.59322
用户设置个人签名 | 4 | 7 | 11 | 0.98743 | 6 | 1.0256 | 8 | 1.4235 | 0.40318
用户设置个人信息 | 4 | 2 | 6 | 0.5386 | 2 | 0.34188 | 6 | 1.0676 | 0.38212
用户绑定手机号 | 2 | 5 | 7 | 0.62837 | 7 | 1.1966 | 8 | 1.4235 | 0.23983
用户找回密码 | 5 | 9 | 14 | 1.2567 | 3 | 0.51282 | 8 | 1.4235 | 0.64904
用户修改密码 | 1 | 9 | 10 | 0.89767 | 7 | 1.1966 | 4 | 0.71174 | 0.47039
用户修改昵称 | 3 | 9 | 12 | 1.0772 | 4 | 0.68376 | 2 | 0.35587 | 1.0361
用户修改头像 | 3 | 2 | 5 | 0.44883 | 8 | 1.3675 | 2 | 0.35587 | 0.26044
用户修改个性签名 | 5 | 1 | 6 | 0.5386 | 6 | 1.0256 | 7 | 1.2456 | 0.23714
用户修改个人信息 | 6 | 2 | 8 | 0.71813 | 8 | 1.3675 | 8 | 1.4235 | 0.2573
退出登录 | 7 | 6 | 13 | 1.167 | 9 | 1.5385 | 4 | 0.71174 | 0.5186
用户个人资源空间上传资源 | 6 | 2 | 8 | 0.71813 | 3 | 0.51282 | 3 | 0.53381 | 0.68614
用户个人资源空间下载资源 | 2 | 9 | 11 | 0.98743 | 9 | 1.5385 | 3 | 0.53381 | 0.4765
用户播放视频 | 7 | 6 | 13 | 1.167 | 6 | 1.0256 | 8 | 1.4235 | 0.47648
用户查看文档资源 | 5 | 2 | 7 | 0.62837 | 6 | 1.0256 | 7 | 1.2456 | 0.27667
用户查看课件资源 | 9 | 7 | 16 | 1.4363 | 7 | 1.1966 | 6 | 1.0676 | 0.63434
用户收藏板块 | 8 | 4 | 12 | 1.0772 | 3 | 0.51282 | 8 | 1.4235 | 0.55632
用户取消收藏板块 | 1 | 5 | 6 | 0.5386 | 8 | 1.3675 | 7 | 1.2456 | 0.20612
用户在板块中发布普通帖子 | 8 | 9 | 17 | 1.526 | 3 | 0.51282 | 3 | 0.53381 | 1.458
用户在板块中发布资源帖子 | 6 | 2 | 8 | 0.71813 | 2 | 0.34188 | 2 | 0.35587 | 1.0292
用户在帖子中回复 | 6 | 2 | 8 | 0.71813 | 1 | 0.17094 | 6 | 1.0676 | 0.57981
用户回复已有回复 | 2 | 5 | 7 | 0.62837 | 6 | 1.0256 | 6 | 1.0676 | 0.30019
用户在楼中楼内回复用户 | 2 | 9 | 11 | 0.98743 | 4 | 0.68376 | 4 | 0.71174 | 0.70758
用户在帖子内选择“只看楼主” | 8 | 7 | 15 | 1.3465 | 8 | 1.3675 | 7 | 1.2456 | 0.51529
用户排序帖子回复，按回复时间倒序排序 | 1 | 1 | 2 | 0.17953 | 9 | 1.5385 | 2 | 0.35587 | 0.094774
用户排序帖子回复，按回复时间正序排序 | 3 | 6 | 9 | 0.8079 | 2 | 0.34188 | 2 | 0.35587 | 1.1579
用户排序帖子回复，按点赞数排序 | 3 | 1 | 4 | 0.35907 | 4 | 0.68376 | 3 | 0.53381 | 0.2949
用户查看原图 | 6 | 2 | 8 | 0.71813 | 5 | 0.8547 | 4 | 0.71174 | 0.45845
用户保存图片 | 8 | 4 | 12 | 1.0772 | 8 | 1.3675 | 8 | 1.4235 | 0.38595
用户删除自己发布的帖子 | 5 | 1 | 6 | 0.5386 | 4 | 0.68376 | 1 | 0.17794 | 0.62505
用户点赞帖子 | 5 | 6 | 11 | 0.98743 | 3 | 0.51282 | 5 | 0.88968 | 0.70405
用户取消点赞帖子 | 2 | 1 | 3 | 0.2693 | 1 | 0.17094 | 8 | 1.4235 | 0.1689
用户点赞回复 | 7 | 8 | 15 | 1.3465 | 9 | 1.5385 | 8 | 1.4235 | 0.4546
用户取消点赞回复 | 5 | 8 | 13 | 1.167 | 6 | 1.0256 | 6 | 1.0676 | 0.55749
用户收藏帖子 | 3 | 7 | 10 | 0.89767 | 7 | 1.1966 | 7 | 1.2456 | 0.36757
用户取消收藏帖子 | 8 | 2 | 10 | 0.89767 | 6 | 1.0256 | 6 | 1.0676 | 0.42884
用户分享帖子 | 6 | 2 | 8 | 0.71813 | 5 | 0.8547 | 5 | 0.88968 | 0.41168
用户分享板块 | 4 | 7 | 11 | 0.98743 | 5 | 0.8547 | 7 | 1.2456 | 0.47015
用户@其他用户 | 8 | 3 | 11 | 0.98743 | 2 | 0.34188 | 2 | 0.35587 | 1.4152
用户下载资源帖子的资源 | 1 | 1 | 2 | 0.17953 | 9 | 1.5385 | 4 | 0.71174 | 0.079785
用户把资源帖子的资源添加到个人资源空间 | 2 | 8 | 10 | 0.89767 | 3 | 0.51282 | 1 | 0.17794 | 1.2995
用户查看收藏的资源帖子 | 8 | 5 | 13 | 1.167 | 1 | 0.17094 | 3 | 0.53381 | 1.6559
用户查看收藏帖子 | 9 | 3 | 12 | 1.0772 | 9 | 1.5385 | 5 | 0.88968 | 0.44363
用户通过ID搜索用户 | 9 | 1 | 10 | 0.89767 | 6 | 1.0256 | 2 | 0.35587 | 0.64977
用户查看其它用户个人信息 | 5 | 3 | 8 | 0.71813 | 3 | 0.51282 | 8 | 1.4235 | 0.37088
用户添加好友 | 3 | 8 | 11 | 0.98743 | 1 | 0.17094 | 7 | 1.2456 | 0.6971
用户删除好友 | 3 | 5 | 8 | 0.71813 | 1 | 0.17094 | 1 | 0.17794 | 2.0584
用户查看信息 | 4 | 7 | 11 | 0.98743 | 1 | 0.17094 | 1 | 0.17794 | 2.8303
用户拉黑其他用户 | 5 | 6 | 11 | 0.98743 | 9 | 1.5385 | 6 | 1.0676 | 0.3789
用户给好友发送私信 | 4 | 6 | 10 | 0.89767 | 3 | 0.51282 | 6 | 1.0676 | 0.56799
用户给非好友发送私信 | 4 | 1 | 5 | 0.44883 | 8 | 1.3675 | 1 | 0.17794 | 0.29042
用户在私信中发送图片 | 2 | 5 | 7 | 0.62837 | 9 | 1.5385 | 9 | 1.6014 | 0.20012
用户在私信中发送个人资源空间内的资源 | 3 | 9 | 12 | 1.0772 | 6 | 1.0256 | 2 | 0.35587 | 0.77972
用户在私信中发送本地资源、文件 | 2 | 7 | 9 | 0.8079 | 2 | 0.34188 | 8 | 1.4235 | 0.45764
用户举报私信消息 | 7 | 5 | 12 | 1.0772 | 8 | 1.3675 | 5 | 0.88968 | 0.47723
用户在群聊内发送文字 | 3 | 2 | 5 | 0.44883 | 8 | 1.3675 | 2 | 0.35587 | 0.26044
用户在群聊内发送图片 | 2 | 8 | 10 | 0.89767 | 8 | 1.3675 | 7 | 1.2456 | 0.34353
用户在群聊内@他人 | 9 | 2 | 11 | 0.98743 | 9 | 1.5385 | 8 | 1.4235 | 0.33337
用户在群聊内发送个人资源空间内的资源 | 3 | 9 | 12 | 1.0772 | 5 | 0.8547 | 2 | 0.35587 | 0.88983
用户在群聊内发送本地资源、文件 | 5 | 9 | 14 | 1.2567 | 4 | 0.68376 | 6 | 1.0676 | 0.71757
用户举报群聊消息 | 1 | 2 | 3 | 0.2693 | 1 | 0.17094 | 8 | 1.4235 | 0.1689
用户创建群聊 | 5 | 1 | 6 | 0.5386 | 5 | 0.8547 | 9 | 1.6014 | 0.21929
用户邀请好友加入群聊 | 9 | 8 | 17 | 1.526 | 5 | 0.8547 | 9 | 1.6014 | 0.62132
用户查看私信 | 8 | 2 | 10 | 0.89767 | 5 | 0.8547 | 2 | 0.35587 | 0.74152
用户进入首页 | 5 | 5 | 10 | 0.89767 | 6 | 1.0256 | 4 | 0.71174 | 0.51668
用户进入某一板块 | 4 | 7 | 11 | 0.98743 | 8 | 1.3675 | 5 | 0.88968 | 0.43746
用户查看板块资源 | 7 | 8 | 15 | 1.3465 | 8 | 1.3675 | 8 | 1.4235 | 0.48244
用户查看板块帖子 | 7 | 5 | 12 | 1.0772 | 8 | 1.3675 | 6 | 1.0676 | 0.44236
用户查看板块热门帖子 | 3 | 4 | 7 | 0.62837 | 6 | 1.0256 | 3 | 0.53381 | 0.40294
用户全局搜索帖子 | 6 | 9 | 15 | 1.3465 | 9 | 1.5385 | 8 | 1.4235 | 0.4546
用户在板块中搜索帖子 | 8 | 5 | 13 | 1.167 | 5 | 0.8547 | 2 | 0.35587 | 0.96398
用户全局排序帖子 | 5 | 4 | 9 | 0.8079 | 2 | 0.34188 | 6 | 1.0676 | 0.57318
用户在板块中排序帖子 | 8 | 1 | 9 | 0.8079 | 9 | 1.5385 | 8 | 1.4235 | 0.27276
用户全局筛选帖子 | 2 | 2 | 4 | 0.35907 | 4 | 0.68376 | 1 | 0.17794 | 0.4167
用户在板块中筛选帖子 | 7 | 8 | 15 | 1.3465 | 8 | 1.3675 | 9 | 1.6014 | 0.45353
用户关注板块 | 9 | 7 | 16 | 1.4363 | 6 | 1.0256 | 9 | 1.6014 | 0.54672
用户关注其他用户 | 8 | 3 | 11 | 0.98743 | 8 | 1.3675 | 2 | 0.35587 | 0.57296
用户拉黑其他用户 | 2 | 1 | 3 | 0.2693 | 3 | 0.51282 | 4 | 0.71174 | 0.21991
用户举报其他用户 | 5 | 7 | 12 | 1.0772 | 8 | 1.3675 | 2 | 0.35587 | 0.62505
用户举报帖子 | 4 | 7 | 11 | 0.98743 | 8 | 1.3675 | 1 | 0.17794 | 0.63893
用户查看友情链接 | 3 | 2 | 5 | 0.44883 | 5 | 0.8547 | 8 | 1.4235 | 0.19701
用户查看APP导向使用指南 | 5 | 5 | 10 | 0.89767 | 3 | 0.51282 | 1 | 0.17794 | 1.2995
用户查看板块资源版面 | 6 | 1 | 7 | 0.62837 | 1 | 0.17094 | 8 | 1.4235 | 0.3941
用户查看版面 | 5 | 7 | 12 | 1.0772 | 9 | 1.5385 | 4 | 0.71174 | 0.47871
用户查看帖子浏览历史 | 4 | 7 | 11 | 0.98743 | 2 | 0.34188 | 3 | 0.53381 | 1.1276
用户按时间排序帖子 | 6 | 1 | 7 | 0.62837 | 3 | 0.51282 | 3 | 0.53381 | 0.60037
用户按回复顺序排序帖子 | 9 | 3 | 12 | 1.0772 | 3 | 0.51282 | 1 | 0.17794 | 1.5594
用户按智能热度顺序排序帖子 | 1 | 2 | 3 | 0.2693 | 6 | 1.0256 | 3 | 0.53381 | 0.17269
用户在首页查看关注板块、用户的新帖子 | 5 | 4 | 9 | 0.8079 | 3 | 0.51282 | 8 | 1.4235 | 0.41724
教师发布无内容长度、图片数量限制的贴子 | 1 | 5 | 6 | 0.5386 | 5 | 0.8547 | 6 | 1.0676 | 0.28018
教师编辑帖子 | 4 | 8 | 12 | 1.0772 | 5 | 0.8547 | 6 | 1.0676 | 0.56037
教师查询用户真实信息 | 3 | 6 | 9 | 0.8079 | 1 | 0.17094 | 7 | 1.2456 | 0.57035
教师进入团队板块进行指导 | 4 | 2 | 6 | 0.5386 | 3 | 0.51282 | 1 | 0.17794 | 0.77972
管理员添加板块 | 2 | 6 | 8 | 0.71813 | 2 | 0.34188 | 4 | 0.71174 | 0.68158
管理员删除板块 | 3 | 5 | 8 | 0.71813 | 1 | 0.17094 | 5 | 0.88968 | 0.67709
管理员修改板块 | 2 | 9 | 11 | 0.98743 | 8 | 1.3675 | 1 | 0.17794 | 0.63893
管理员删除帖子 | 3 | 2 | 5 | 0.44883 | 6 | 1.0256 | 9 | 1.6014 | 0.17085
管理员发布全局通知 | 7 | 6 | 13 | 1.167 | 6 | 1.0256 | 1 | 0.17794 | 0.96958
管理员发布板块通知 | 2 | 9 | 11 | 0.98743 | 1 | 0.17094 | 2 | 0.35587 | 1.8744
管理员在论坛板块中置顶帖子 | 2 | 8 | 10 | 0.89767 | 8 | 1.3675 | 6 | 1.0676 | 0.36863
管理员在论坛板块中置顶帖子 | 3 | 6 | 9 | 0.8079 | 2 | 0.34188 | 3 | 0.53381 | 0.92259
管理员解封用户 | 2 | 3 | 5 | 0.44883 | 2 | 0.34188 | 4 | 0.71174 | 0.42599
管理员给板块添加版面 | 1 | 7 | 8 | 0.71813 | 7 | 1.1966 | 2 | 0.35587 | 0.46258
管理员编辑自己的帖子 | 6 | 3 | 9 | 0.8079 | 3 | 0.51282 | 6 | 1.0676 | 0.51119
管理员编辑其他用户的帖子 | 6 | 5 | 11 | 0.98743 | 4 | 0.68376 | 1 | 0.17794 | 1.1459
管理员移动帖子的版面 | 1 | 7 | 8 | 0.71813 | 2 | 0.34188 | 6 | 1.0676 | 0.5095
管理员给帖子设置精品 | 6 | 7 | 13 | 1.167 | 5 | 0.8547 | 1 | 0.17794 | 1.1301
管理员解散群聊 | 2 | 9 | 11 | 0.98743 | 2 | 0.34188 | 6 | 1.0676 | 0.70056
游客注册 | 7 | 5 | 12 | 1.0772 | 7 | 1.1966 | 8 | 1.4235 | 0.41113
游客浏览帖子 | 3 | 7 | 10 | 0.89767 | 2 | 0.34188 | 2 | 0.35587 | 1.2865
游客浏览资源 | 5 | 5 | 10 | 0.89767 | 5 | 0.8547 | 8 | 1.4235 | 0.39403
| 531 | 583 | 1114 | 100 | 585 | 100 | 562 | 100 | 70.6404

## Template
Relative Weights: | 1 | 1 |  |  | 1 |  | 1
Feature | Relative Benefit | Relative Penalty | Total Value | Value % | Relative Cost | Cost % | Relative Risk | Risk % | Priority
<List each feature, requirement, or use case to be prioritized |  |  | 0 | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0!
in these cells, one item per cell. Copy and insert additional |  |  | 0 | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0!
rows as needed; the formulas will adjust automatically.> |  |  | 0 | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0!
|  |  | 0 | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0!
Totals | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0!

## Example
Relative Weights: | 2 | 1 |  |  | 1 |  | 0.5
Feature | Relative Benefit | Relative Penalty | Total Value | Value % | Relative Cost | Cost % | Relative Risk | Risk % | Priority
Print a material safety data sheet | 2 | 4 | 8 | 5.1613 | 1 | 2.7027 | 1 | 3.0303 | 1.2237
Query status of a vendor order | 5 | 3 | 13 | 8.3871 | 2 | 5.4054 | 1 | 3.0303 | 1.2119
Generate a Chemical Stockroom inventory report | 9 | 7 | 25 | 16.129 | 5 | 13.5135 | 3 | 9.0909 | 0.89313
See history of a specific chemical container | 5 | 5 | 15 | 9.6774 | 3 | 8.1081 | 2 | 6.0606 | 0.86883
Search vendor catalogs for a specific chemical | 9 | 8 | 26 | 16.7742 | 3 | 8.1081 | 8 | 24.2424 | 0.8292
Maintain a list of hazardous chemicals | 3 | 9 | 15 | 9.6774 | 3 | 8.1081 | 4 | 12.1212 | 0.68301
Modify a pending chemical request | 4 | 3 | 11 | 7.0968 | 3 | 8.1081 | 2 | 6.0606 | 0.63714
Generate an individual laboratory inventory report | 6 | 2 | 14 | 9.0323 | 4 | 10.8108 | 3 | 9.0909 | 0.58818
Check training database for hazardous chemical training record | 3 | 4 | 10 | 6.4516 | 4 | 10.8108 | 2 | 6.0606 | 0.46612
Import chemical structures from structure drawing tools | 7 | 4 | 18 | 11.6129 | 9 | 24.3243 | 7 | 21.2121 | 0.33246
Totals | 53 | 49 | 155 | 100 | 37 | 100 | 33 | 100

## Multiple Stakeholders
Relative Weights: | 3 |  | 1 |  | 1 |  | 1 | 1 |  |  | 1 |  | 1
| Stakeholder 1 |  | Stakeholder 2 |  | Stakeholder 3
Feature | Relative Benefit | Relative Penalty | Relative Benefit | Relative Penalty | Relative Benefit | Relative Penalty | Total Benefit | Total Penalty | Total Value | Value % | Relative Cost | Cost % | Relative Risk | Risk % | Priority
Query status of a vendor order | 7 | 3 | 5 | 3 | 5 | 3 | 6.2 | 3 | 9.2 | 9.4262 | 2 | 4.7619 | 1 | 3.0303 | 1.2097
Generate a Chemical Stockroom inventory report | 3 | 7 | 9 | 7 | 9 | 7 | 5.4 | 7 | 12.4 | 12.7049 | 5 | 11.9048 | 3 | 9.0909 | 0.60512
See history of a specific chemical container | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 10 | 10.2459 | 3 | 7.1429 | 2 | 6.0606 | 0.776
Print a chemical safety datasheet | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 3.0738 | 1 | 2.381 | 1 | 3.0303 | 0.56803
Maintain a list of hazardous chemicals | 4 | 9 | 4 | 9 | 4 | 9 | 4 | 9 | 13 | 13.3197 | 4 | 9.5238 | 4 | 12.1212 | 0.61537
Modify a pending chemical request | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 7 | 7.1721 | 3 | 7.1429 | 2 | 6.0606 | 0.5432
Generate an individual laboratory inventory report | 6 | 2 | 6 | 2 | 6 | 2 | 6 | 2 | 8 | 8.1967 | 4 | 9.5238 | 3 | 9.0909 | 0.44034
Search vendor catalogs for a specific chemical | 9 | 8 | 9 | 8 | 9 | 8 | 9 | 8 | 17 | 17.418 | 7 | 16.6667 | 8 | 24.2424 | 0.42577
Check training database for hazardous chemical training record | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 7 | 7.1721 | 4 | 9.5238 | 2 | 6.0606 | 0.46021
Import chemical structures from structure drawing tools | 7 | 4 | 7 | 4 | 7 | 4 | 7 | 4 | 11 | 11.2705 | 9 | 21.4286 | 7 | 21.2121 | 0.26431
Totals | 50 | 46 | 54 | 46 | 54 | 46 | 51.6 | 46 | 97.6 | 100 | 42 | 100 | 33 | 100